Project Plan

GBCMart

| Industry Partner | N/A |
| --- | --- |
| Primary Instructor | Laily Ajellu |
| Team Member | Woohyuk (Harry) Song |
| Team Member | Iqbal Qureshi |
| Team Member | Mitchell Stevenson |
| Team Member | Harrison Pape |
| Team Member | Amelework Murti |

Document Revision History

| Revision # | Date |
| --- | --- |
| 3.0 | February 12th, 2026 |

Table of Contents

1. Executive Summary	3

2. Project Approvers, Reviews and Distribution List	4

3. Scope	5

4. Deliverables	5

5. Assumptions	5

6. Dependencies	5

7. Risk Management	6

8. Communication	6

9. Task Listing (WBS- Work Breakdown Structure)	7

10. Gantt Chart	7

11. Milestones	7

12. RAM – Responsibility Assignment Matrix	8

13. Approval	8

# 1. Executive Summary

The following describes the project to be executed.

| Objective | Develop a web-based application that aggregates store flyers, enabling users to create, search, filter, and export personalized shopping lists with secure login and storage for a convenient and interactive shopping experience. |
| --- | --- |
| Corporate Goals Addressed | Efficiency, User friendly Interface, Time saving. |
| Planned Start Date | September 08, 2025 |
| Planned End Date | April 01, 2026 |

# 2. Project Approvers, Reviews and Distribution List

Approvers, reviewers and distribution list

| Project Role | Name | E-mail | Date |
| --- | --- | --- | --- |
| Instructor | Laily Ajellu | Laily.Ajellu@georgebrown.ca | February 12, 2026 |
| Back-End Developer | Woohyuk (Harry) Song | Harry.Song@georgebrown.ca | February 12, 2026 |
| Full-Stack developer | Iqbal Qureshi | Iqbal.Qureshi@georgebrown.ca | February 12, 2026 |
| Database manager | Mitchell Stevenson | Mitchell.Stevenson@georgebrown.ca | February 12, 2026 |
| Project leader | Harrison Pape | Harrison.Pape@georgebrown.ca | February 12, 2026 |
| Front- End developer | Amelework Murti | Amelework.Murti@georgebrown.ca | February 12, 2026 |

# 3. Scope

Define the sum total of all of its products and their requirements or features.

| In Scope | Out of Scope |
| --- | --- |
| Collect and compile store flyer information from online sources. | Deploying the platform for full public use at this stage. |
| Allow users to create accounts and sign into the application. | Supporting online purchasing or checkout features. |
| Enable users to add products to a shopping list that can be shared. | Allowing users to import new store flyers via custom URLs. |
| Provide a Help/About section with guidance and details about the app. | Incorporating advertisements into the application. |
| Display multiple grocery store options using a user-friendly tab layout. | Offering subscription-based or pain upgrades. |
| Ensure the interface is optimized for use on mobile devices. |  |

# 4. Deliverables

This project will deliver the following.

| Deliverable | Description |
| --- | --- |
| Database | The web app will collect promotional pricing information from multiple retailers and present it in a single, user friendly interface. |
| List creation | Users will be able to build a dynamic shopping list where items can be added or removed. |
| Data Export | The system will provide option to save the shopping list on the users device. |
| Search Function | Search and filtering tools will be included. |
| User Accounts | A secure account registration will be implemented so users have customised experience. |
| Pricing History | When the system record product pricing, it allows users to compare the prices from before. |

# 5. Assumptions

This project makes the following assumptions;

- Store flyer and promotional pricing information will remain publicly available in formats that include details such as product descriptions, sale, and categories.

- The flyer data will be structured in a way that allows for semi-automated retrieval and frequent updates without requiring extensive manual intervention.

- Users will be willing to create secure  accounts in order to personalize their experience.

- Users will trust that the system follows appropriate security measures to safeguard their account information.

- Internet access will be available for users while browsing the application.

- The retailers whose information we display will update their flyers regularly.

- The team will have sufficient time and collaborations.

# 6. Dependencies

The following are the internal and external dependencies that will have to be acknowledged and addressed;

-  Consistent Access to Flyer Data-External

The Application relies on grocery retailers making promotional data publicly available online.

-Network Connectivity-External

Users must have internet access for the system to retrieve up-to-date pricing information.

- Hosting and Backend Services – External/Internal
A stable deployment environment is needed to support account features, databases, and application testing.

- Device and browser compatibility – External
The app depends on users accessing the system from supported browsers and mobile devices.

- Retailer update frequency – External
The accuracy of sale information depends on stores updating their pricing and flyers regularly

- Team Skillsets and development tools – Internal
The team must have access to necessary tools, version control systems, and the technical expertise to complete the project.

- Database reliability – Internal
The data storage used for user accounts, shopping lists, and price history must function without interruption.

- Third-Party tools and libraries – External
Continued support for data scraping, authentication services, and UI frameworks is required.

# 7. Risk Management

| Potential Risk | Severity (H/M/L) | Likelihood (H/M/L) | Management Strategy |
| --- | --- | --- | --- |
| Data source become inaccessible | H | M | Refine the strategy to include implementing a monitoring system to alert the team of structural changes in retail domains |
| Security vulnerabilities with user accounts | H | L | We would use secure authentication frameworks and enforce encryption. |
| Lack of experience with certain technologies | M | H | Assign tasks based on strength and allocate enough time to learn. |
| Outdated pricing data displayed | M | M | Schedule automated refresh cycles and maintain data validation checks |
| User interface(UI) issues | L | M | Since the UI is roughly complete in terms of navigating between the pages, change the focus to usability testing, feedback, and bug fixing |
| Users not wanting to create accounts | L | M | Offering guest mode and highlight the benefit of account features. |
| Testing Pool Size | L | M | Mitigated by utilizing automated unit tests to compensate for the small feedback group |

# 8. Communication

Reporting

The following reports will be produced;

| Report | Audience | Frequency |
| --- | --- | --- |
| Project Summary / Vision | Instructor | Once |
| High-Level Business Requirements | Instructor | Once |
| Personas & User Stories | Instructor | Once |
| Project Plan & Team Charter | Instructor | Monthly, as needed |
| Software Requirements Analysis & Design | Instructor | Once |
| Product & Sprint Backlogs | Instructor | Updated per Sprint cycle |
| Tech Requirements & Learning Plan | Instructor | Once |
| Interactive Figma Prototype | Instructor | Once |
| Meeting Minutes (MoM #1 – #8) | Instructor | Weekly/Bi-Weekly |
| Project Status Reports (I, II, III) | Instructor | Monthly, as needed |

Meetings

The following meetings/communication will be established;

| Meeting | Purpose | Attendees | Frequency |
| --- | --- | --- | --- |
| Weekly Status Meeting | Review tasks, assign responsibilities, and address issues | Entire Team | Weekly (Tuesdays) |
| Discord Group Chat | Daily ad-hoc communication, intermittent progress updates, and quick queries. | Entire Team | Continuous |
| GitHub Repository | Version control, code modification, and tracking progress of files. | Entire Team | Continuous |

# 9. Task Listing (WBS- Work Breakdown Structure)

The following resource proposal template summarizes the resource hours committed to this project, upon final approval of this document.

| Reference | Tasks | Duration | Dependency | Complete |
| --- | --- | --- | --- | --- |
| A | Requirements gathering and finalizing Project Scope | 1 week | NONE | 100% |
| B | System design(UI wireframes, database design…) | 2 weeks | A | 100% |
| C | Front-end Development (UI implementation and responsive design) | 2 weeks | B | 70% |
| D | Back-end development(Database, API, account system) | 3 weeks | B | 50% |
| E | Flyer data integration(scraping store data) | 2 weeks | D | 0% |
| F | Testing (unit testing, usability testing, bug fixes) | 2 weeks | C & E | 0% |

# 10. Gantt Chart

Create a detailed Gantt Chart from your Task Listing(Use any software tool and paste the image or upload as a separate file that can be opened as pdf/doc/xls)

Below is an example:

| Task | Period |  |  |  |  |  |  |  |  |  | Completed |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dates | Dates | Dates | Dates | Dates | Dates | Dates | Dates | Dates | Dates |  |

# 11. Milestones

| Major Activity or Milestone | Estimated Milestone Target date | Owner/Reviewer Team Members |
| --- | --- | --- |
| Project scope and requirements approved | Oct 26, 2025- Jan 10, 2026 | Instructor |
| Wireframes and UI/UX design completed | January 24, 2026 | Front-End lead |
| Front-End development phase completed | February 7, 2026 | Front-End lead |
| Back-end APIs and integrations completed | February 21, 2026 | Back-End lead |
| Final submission and Demonstration | April 10,26 | Entire team and Instructor |

# 12. RAM – Responsibility Assignment Matrix

Create a RAM from your Task Listing. A sample is shown below:

# 13. Approval

The signatures below indicate their approval of the contents of this document.

| Project Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Back-End Developer | Woohyuk (Harry) Song | H.S | Feb 12, 2026 |
| Full Stack Developer | Iqbal Qureshi | I.Q | Oct 23, 2025 |
| Database Manager | Mitchell Stevenson | M.S | Feb 12, 2026 |
| Project Leader | Harrison Pape | H.P | Feb 12, 2026 |
| Front-End Developer | Amelework Murti | A.M | Feb 12, 2026 |